## Test Requirements
General Information
Project
Test Designed By |  |  | Reviewed By
Test Designed Date |  |  | Reviewed Date
List of Test Requirements
No. | Test Requirement ID | Test Requirement Description | Note
1 | F.5.1 | Verify that when a product is added to the cart, its information is displayed on the user's cart interface
2 | F.5.2 | Verify the behavior when a product is removed from the cart
3 | F.5.2 | Verify the behavior when multiple products are removed from the cart
4 | F.5.3 | Verify the system's response when entering a negative quantity for a product
5 | F.5.3 | Verify the system's response when entering a large quantity for a product
6 | F.5.4 | Verify that products added to the cart include complete and clearly displayed information
7 | F.3.1 | Verify all products are fully displayed on the book management interface
8 | F.3.2 | Verify the product sorting feature is properly and accurately arranged as required on the book management interface
9 | F.3.3 | Verify the pagination feature of the book management page
10 | F.3.4 | View book list when no books are available
11 | F.3.5 | Verify the new book creation feature in the book management page
12 | F.3.6 | Verify the feature of creating new books with invalid information on the book management page
13 | F.3.7 | Verify the feature of creating new books with information identical to existing products in the book management page
14 | F.3.8 | Verify available book update feature with valid details
15 | F.3.9 | Verify available book update feature with invalid details
16 | F.3.10 | Verify the functionality to successfully delete an existing book

## IntegratedBookManagement
No. | Test Requirement ID | Test Case ID | Test Objective | Pre-conditions | Step # | Step Action | Test Data | Expected Result | Notes
1 | F.3.1 | B_01 | Verify all products are fully displayed on the book management interface | Log in to an account with admin rights with the role 'ThuKho' | 1 | Open login page | http://localhost:5173/sign-in
[5 empty] | 2 | Enter a valid email + valid password | email: phuc@gmail.com pass: 123456
[5 empty] | 3 | Press button <Đăng nhập> |  | Login successfully "Đăng nhập thành công" and go to home page
[5 empty] | 4 | Hover over the user icon which will show a popup and click on the "Quản lý hệ thống" button |  | The website will move to the admin page
[5 empty] | 5 | Click "Sản phẩm" to open book management page |  | Book management page is displayed
[5 empty] | 6 | View full list of books |  | The book list is displayed completely and accurately
2 | F.3.2 | B_02 | Verify the product sorting feature is properly and accurately arranged as required on the book management interface | There are more than one product in the book management, and the admin is logged in | 1 | Open login page | http://localhost:5173/sign-in
[5 empty] | 2 | Enter a valid email + valid password | email: phuc@gmail.com pass: 123456
[5 empty] | 3 | Press button <Đăng nhập> |  | Login successfully "Đăng nhập thành công" and go to home page
[5 empty] | 4 | Hover over the user icon which will show a popup and click on the "Quản lý hệ thống" button |  | The website will move to the admin page
[5 empty] | 5 | Click "Sản phẩm" to open book management page |  | Book management page is displayed
[5 empty] | 6 | Apply sort by price/ category |  | Sorted books displayed based on category or price
[5 empty] | 7 | Check that the interface of the book management page is arranged correctly as required |  | The sort function performs correctly
3 | F.3.3 | B_03 | Verify the pagination feature of the book management page | There are more than one product in the book management, and the admin is logged in | 1 | Open login page | http://localhost:5173/sign-in
[5 empty] | 2 | Enter a valid email + valid password | email: phuc@gmail.com pass: 123456
[5 empty] | 3 | Press button <Đăng nhập> |  | Login successfully "Đăng nhập thành công" and go to home page
[5 empty] | 4 | Hover over the user icon which will show a popup and click on the "Quản lý hệ thống" button |  | The website will move to the admin page
[5 empty] | 5 | Click "Sản phẩm" to open book management page |  | Book management page is displayed
[5 empty] | 6 | Check that the product listing page's pagination is correctly paginated |  | The pagination feature has been performed correctly, dividing all 10 books into 1 page
4 | F.3.4 | B_04 | View book list when no books are available | There are no books in book management and the admin is logged in | 1 | Open login page | http://localhost:5173/sign-in
[5 empty] | 2 | Enter a valid email + valid password | email: phuc@gmail.com pass: 123456
[5 empty] | 3 | Press button <Đăng nhập> |  | Login successfully "Đăng nhập thành công" and go to home page
[5 empty] | 4 | Hover over the user icon which will show a popup and click on the "Quản lý hệ thống" button |  | The website will move to the admin page
[5 empty] | 5 | Click "Sản phẩm" to open book management page |  | Book management page is displayed
[5 empty] | 6 | View book management page when no books in there |  | No books displayed
5 | F.3.5 | CB_01 | Verify the new book creation feature in the book management page | The admin is logged in | 1 | Open login page | http://localhost:5173/sign-in
[5 empty] | 2 | Enter a valid email + valid password | email: phuc@gmail.com pass: 123456
[5 empty] | 3 | Press button <Đăng nhập> |  | Login successfully "Đăng nhập thành công" and go to home page
[5 empty] | 4 | Hover over the user icon which will show a popup and click on the "Quản lý hệ thống" button |  | The website will move to the admin page
[5 empty] | 5 | Click "Sản phẩm" to open book management page |  | Book management page is displayed
[5 empty] | 6 | Press button <+> |  | Display popup to enter information to create a new book
[5 empty] | 7 | Enter book information | Tên sản phẩm:"1234Days", Loại sản phẩm: "Hình sự", số lượng tồn kho: "5", Giá: "25000", Hình ảnh
[5 empty] | 8 | Press button <submit> to create book |  | The book has been created and appears in product category
6 | F.3.6 | CB_02 | Verify the feature of creating new books with invalid information on the book management page | The admin is logged in | 1 | Open login page | http://localhost:5173/sign-in
[5 empty] | 2 | Enter a valid email + valid password | email: phuc@gmail.com pass: 123456
[5 empty] | 3 | Press button <Đăng nhập> |  | Login successfully "Đăng nhập thành công" and go to home page
[5 empty] | 4 | Hover over the user icon which will show a popup and click on the "Quản lý hệ thống" button |  | The website will move to the admin page
[5 empty] | 5 | Click "Sản phẩm" to open book management page |  | Book management page is displayed
[5 empty] | 6 | Press <+> button |  | Display popup to enter information to create a new book
[5 empty] | 7 | Enter incomplete book details | Giá:"ádasfsdg"
[5 empty] | 8 | Press <Submit> |  | Error message 'Title is required' is displayed
7 | F.3.7 | CB_03 | Verify the feature of creating new books with information identical to existing products in the book management page | The admin is logged in | 1 | Open login page | http://localhost:5173/sign-in
[5 empty] | 2 | Enter a valid email + valid password | email: phuc@gmail.com pass: 123456
[5 empty] | 3 | Press button <Đăng nhập> |  | Login successfully "Đăng nhập thành công" and go to home page
[5 empty] | 4 | Hover over the user icon which will show a popup and click on the "Quản lý hệ thống" button |  | The website will move to the admin page
[5 empty] | 5 | Click "Sản phẩm" to open book management page |  | Book management page is displayed
[5 empty] | 6 | Press <+> button |  | Display popup to enter information to create a new book
[5 empty] | 7 | Enter details of a book with an existing title | Tên sản phẩm:"Dế Mèn Phiêu Lưu Ký 2 "
[5 empty] | 8 | Press <Submit> |  | message 'Thêm sản phẩm thành công!!' is displayed
8 | F.3.8 | UB_01 | Verify available book update feature with valid details | There are more than one product in the book management, and the admin is logged in | 1 | Open login page | http://localhost:5173/sign-in
[5 empty] | 2 | Enter a valid email + valid password | email: phuc@gmail.com pass: 123456
[5 empty] | 3 | Press button <Đăng nhập> |  | Login successfully "Đăng nhập thành công" and go to home page
[5 empty] | 4 | Hover over the user icon which will show a popup and click on the "Quản lý hệ thống" button |  | The website will move to the admin page
[5 empty] | 5 | Click "Sản phẩm" to open book management page |  | Book management page is displayed
[5 empty] | 6 | Select a book to update | Dế Mèn Phiêu Lưu Ký 2
[5 empty] | 7 | Click button "Pen" to update |  | Display popup information of to update information of book
[5 empty] | 8 | Enter new valid details | Tên sản phẩm: "2345Days"
[5 empty] | 9 | Press <Xác nhận> |  | message: "Cập nhật sản phẩm thành công!!"
9 | F.3.9 | UB_02 | Verify available book update feature with invalid details | There are more than one product in the book management, and the admin is logged in | 1 | Open login page | http://localhost:5173/sign-in
[5 empty] | 2 | Enter a valid email + valid password | email: phuc@gmail.com pass: 123456
[5 empty] | 3 | Press button <Đăng nhập> |  | Login successfully "Đăng nhập thành công" and go to home page
[5 empty] | 4 | Hover over the user icon which will show a popup and click on the "Quản lý hệ thống" button |  | The website will move to the admin page
[5 empty] | 5 | Click "Sản phẩm" to open book management page |  | Book management page is displayed
[5 empty] | 6 | Select a book to update | 2345Days
[5 empty] | 7 | Click button "Pen" to update |  | Display popup information of to update information of book
[5 empty] | 8 | Enter invalid details | Giá:"ádasfsdg"
[5 empty] | 9 | Press <Xác nhận> |  | Nothing happens and the book's information cannot be updated
10 | F.3.10 | DB_01 | Verify the functionality to successfully delete an existing book | There are more than one product in the book management, and the admin is logged in | 1 | Open login page | http://localhost:5173/sign-in
[5 empty] | 2 | Enter a valid email + valid password | email: phuc@gmail.com pass: 123456
[5 empty] | 3 | Press button <Đăng nhập> |  | Login successfully "Đăng nhập thành công" and go to home page
[5 empty] | 4 | Hover over the user icon which will show a popup and click on the "Quản lý hệ thống" button |  | The website will move to the admin page
[5 empty] | 5 | Click "Sản phẩm" to open book management page |  | Book management page is displayed
[5 empty] | 6 | Select a book to delete | 2345Days
[5 empty] | 7 | Press <Delete> |  | Display product deletion confirmation popup
[5 empty] | 8 | Press <Ok> |  | message: "Xóa sản phẩm thành công!!"

## Integrated Cart Management
No. | Test Requirement ID | Test Case ID | Test Objective | Pre-conditions | Step # | Step Action | Test Data | Expected Result | Notes
1 | F.5.1 | C_01 | Verify that when a product is added to the cart, its information is displayed on the user's cart interface | There are sufficient products available to add to the cart, and the user must be logged into their account | 1 | Log in to the user account | Email: phuc@gmail.com Pass: 123456
[5 empty] | 2 | Access the homepage | http://localhost:5173/
[5 empty] | 3 | Select a product | book name: Tư Duy Mở price: 79.000 VND
[5 empty] | 4 | Click on the product to view its details
[5 empty] | 5 | Check the detailed product information | book name: Tư Duy Mở price 79.000 VND rate: 5
[5 empty] | 6 | Click button <Mua hàng> | Quantity: 1
[5 empty] | 7 | Click button <Giỏ hàng> | http://localhost:5173/order
[5 empty] | 8 | Verify the product information in the cart | Book name: Tư duy mở Unit Price: 97.000 VNĐ Quantity: 1 pice: 97.000 VNĐ | Displays correct and complete product information
2 | F.5.2 | C_02 | Verify the behavior when a product is removed from the cart | There is at least one product in the cart, and the user is logged in | 1 | Log in to the user account | Email: phuc@gmail.com Pass: 123456
[5 empty] | 2 | Go to the cart page | http://localhost:5173/order
[5 empty] | 3 | Click the red trash icon on the item
[5 empty] | 4 | Check whether the item has been removed from the cart |  | Item is removed from the cart
3 | F.5.2 | C_03 | Verify the behavior when multiple products are removed from the cart | There are more than one product in the cart, and the user is logged in | 1 | Log in to the user account | Email: phuc@gmail.com Pass: 123456
[5 empty] | 2 | Go to the cart page | http://localhost:5173/order
[5 empty] | 3 | Select the checkboxes for at least two items
[5 empty] | 4 | Click the black trash icon on the header of the table |  | Items are removed from the cart
4 | F.5.3 | C_04 | Verify the system's response when entering a negative quantity for a product | There is at least one product in the cart, and the user is logged in | 1 | Log in to the user account | Email: phuc@gmail.com Pass: 123456
[5 empty] | 2 | Go to the cart page | http://localhost:5173/order
[5 empty] | 3 | Click the down arrow in the quantity input of an item
[5 empty] | 4 | Adjust the product quantity to a negative value | Quantity: -20 | Cannot adjust the quantity to a negative number
5 | F.5.3 | C_05 | Verify the system's response when entering a large quantity for a product | There is at least one product in the cart, and the user is logged in | 1 | Log in to the user account | Email: phuc@gmail.com Pass: 123456
[5 empty] | 2 | Go to the cart page | http://localhost:5173/order
[5 empty] | 3 | Click the up arrow in the quantity input of an item
[5 empty] | 4 | Adjust the product quantity to a large number | Quantity: 120 | Cannot adjust the quantity to more than 100
6 | F.5.4 | C_06 | Verify that products added to the cart include complete and clearly displayed information | There is at least one product in the cart, and the user is logged in | 1 | Log in to the user account | Email: phuc@gmail.com Pass: 123456
[5 empty] | 2 | Go to the cart page | http://localhost:5173/order
[5 empty] | 3 | Check whether the cart interface includes all product fields (e.g., name, quantity, price, total, etc.) and ensures clarity of display |  | All product information is complete in the cart

## Integrated Order Management
No. | Test Requirement ID | Test Case ID | Test Objective | Pre-conditions | Step # | Step Action | Test Data | Expected Result | Notes
1 | F.4.1 | Od_01 | Check display of all orders | There is at least one order in the system | 1 | Log in to the user account | Email: phuc@gmail.com Pass: 123456 | Successfully logged in, go to "Trang chủ"
[5 empty] | 2 | Access the homepage | http://localhost:5173 | The system's home page is displayed with the correct interface.
[5 empty] | 3 | Open page "quản lý hệ thống" |  | The "Quản lý hệ thống" page interface was opened successfully.
[5 empty] | 4 | Click "Đơn hàng" |  | Redirect to order list management page.
[5 empty] | 5 | Check out the complete order list display |  | All existing orders in the system are fully displayed, including columns: Buyer name, Phone number, Order status, Payment,...
[5 empty] | 6 | Scroll down to check out the pagination |  | If the number of orders exceeds 10/page, the system displays pagination. Users can click to switch pages without error.
[5 empty] | 7 | Check the information of each order |  | Choose a random order, check the displayed information: Buyer name, Phone number, Payment, Order status, Address,...
2 | F.4.2 | Od_02 | Update order status successfully | Order status is "Đang xử lý " | 1 | Open login page | http://localhost:5173/sign-in
[5 empty] | 2 | Enter a valid email + valid password | email: phuc@gmail.com pass: 123456
[5 empty] | 3 | Press button <Đăng nhập> |  | Successfully logged in, go to "Trang chủ"
[5 empty] | 4 | Access the homepage |  | The system's home page is displayed with the correct interface.
[5 empty] | 5 | Open page "quản lý hệ thống" |  | The "Quản lý hệ thống" page interface was opened successfully.
[5 empty] | 6 | Click "Đơn hàng" |  | Redirect to order list management page.
[5 empty] | 7 | Select the order whose status needs to be updated | Tên người mua: Phuc Số điện thoại: 0321321 | The order displays correctly in the list
[5 empty] | 8 | Click the "Tình trạng đơn hàng" button | New status: "Đang giao hàng" | The interface displays a status update confirmation message
3 | F.4.3 | Od_03 | Test the ability to filter orders by date | There are orders on many different days | 1 | Log in to the user account | Email: phuc@gmail.com Pass: 123456 | Successfully logged in, go to "Trang chủ"
[5 empty] | 2 | Access the homepage | http://localhost:5173 | The system's home page is displayed with the correct interface.
[5 empty] | 3 | Open page "quản lý hệ thống" |  | The "Quản lý hệ thống" page interface was opened successfully.
[5 empty] | 4 | Click "Đơn hàng" |  | Redirect to order list management page.
[5 empty] | 5 | click "Ngày tạo" |  | The order list is sorted from oldest date to newest date
[5 empty] | 6 | Check if orders are filtered by date | From the oldest date to the newest date | The list displays orders from oldest date to newest date
[5 empty] | 7 | click again "Ngày tạo" |  | The order list is sorted from newest to oldest date
4 | F.4.4 | Od_04 | Check the ability to update the payment status of your order | The order already exists in the system with the current payment status "Chưa thanh toán" | 1 | Log in to the administrator account | Email: phuc@gmail.com Pass: 123456 | Successfully logged in, go to "Trang chủ"
[5 empty] | 2 | Access the homepage | http://localhost:5173 | The system's home page is displayed with the correct interface.
[5 empty] | 3 | Open page "quản lý hệ thống" |  | The "Quản lý hệ thống" page interface was opened successfully.
[5 empty] | 4 | Click "Đơn hàng" |  | Redirect to order list management page.
[5 empty] | 5 | Find and select the order whose payment status needs to be updated | Tên người mua: Phuc Số điện thoại: 0321321
[5 empty] | 6 | Click "Chưa thanh toán"
[5 empty] | 7 | Select the new payment status from the list | New status: "Đã thanh toán" | The new state is selected and ready to update.
[5 empty] | 8 | Return to the order list and check the updated order's payment status |  | The order's payment status displays as "Đã thanh toán"
5 | F.4.5 | Od_05 | Check the order list interface | The system contains at least 10 orders with different statuses | 1 | Log in to the administrator account | Email: phuc@gmail.com Pass: 123456 | Successfully logged in, go to "Trang chủ"
[5 empty] | 2 | Access the homepage | http://localhost:5173 | The system's home page is displayed with the correct interface.
[5 empty] | 3 | Open page "quản lý hệ thống" |  | The "Quản lý hệ thống" page interface was opened successfully.
[5 empty] | 4 | Click "Đơn hàng" |  | The order list is fully displayed with current statuses
[5 empty] | 5 | Check that the order list displays the correct information columns |  | The list interface displays the correct columns: Buyer name, Phone number, Order status, Payment, Order total, Delivery fee, Address, City, Discount rate, Discount code, Created Date, Updated Date, Payment Method
[5 empty] | 6 | Check the pagination display when the number of orders is greater than the limit | The list contains 25 orders | The system displays correct pagination (10 single pages each, 3 pages total)
6 | F.4.6 | Od_06 | Test the ability to export order management files | The system contains at least 20 orders with complete information | 1 | Log in to the administrator account | Email: phuc@gmail.com Pass: 123456 | Successfully logged in, go to "Trang chủ"
[5 empty] | 2 | Access the homepage | http://localhost:5173 | The system's home page is displayed with the correct interface.
[5 empty] | 3 | Open page "quản lý hệ thống" |  | The "Quản lý hệ thống" page interface was opened successfully.
[5 empty] | 4 | Click "Đơn hàng" |  | The order list is fully displayed with current statuses
[5 empty] | 5 | Click button "Xuất file" |  | The system automatically exports Excel file reports to the computer
[5 empty] | 6 | Save the report file to your computer | File Name: orders_report.xlsx | The file contains complete order list information: Buyer name, Phone number, Order status, Payment, ...

## Test Executed Report
Test case ID | Mô tả Test Objective | Chức năng | Trạng thái | Kết quả Thực thi
B_01 | Verify all products are fully displayed on the book management interface | Book Management | pass | Thành công
B_02 | Verify the product sorting feature is properly and accurately arranged as required on the book management interface | Book Management | pass | Thành công
B_03 | Verify the pagination feature of the book management page | Book Management | pass | Thành công
B_04 | View book list when no books are available | Book Management | pass | Thành công
CB_01 | Verify the new book creation feature in the book management page | Book Management | pass | Thành công
CB_02 | Verify the feature of creating new books with invalid information on the book management page | Book Management | pass | Thành công
CB_03 | Verify the feature of creating new books with information identical to existing products in the book management page | Book Management | pass | Thành công
UB_01 | Verify available book update feature with valid details | Book Management | pass | Thành công
UB_02 | Verify available book update feature with invalid details | Book Management | pass | Thành công
DB_01 | Verify the functionality to successfully delete an existing book | Book Management | pass | Thành công
C_01 | Verify that when a product is added to the cart, its information is displayed on the user's cart interface | Cart Management | pass | Thành công
C_02 | Verify the behavior when a product is removed from the cart | Cart Management | pass | Thành công
C_03 | Verify the behavior when multiple products are removed from the cart | Cart Management | pass | Thành công
C_04 | Verify the system's response when entering a negative quantity for a product | Cart Management | pass | Thành công
C_05 | Verify the system's response when entering a large quantity for a product | Cart Management | pass | Thành công
C_06 | Verify that products added to the cart include complete and clearly displayed information | Cart Management | pass | Thành công
Od_01 | Check display of all orders | Orders Management | pass | Thành công
Od_02 | Update order status successfully | Orders Management | pass | Thành công
Od_03 | Test the ability to filter orders by date | Orders Management | pass | Thành công
Od_04 | Check the ability to update the payment status of your order | Orders Management | pass | Thành công
Od_05 | Check the order list interface | Orders Management | pass | Thành công
Od_06 | Test the ability to export order management files | Orders Management | pass | Thành công
NG_01 | Check the user list appears | User Management | pass | Thành công
NG_02 | User detailed information appears | User Management | pass | Thành công
NG_03 | The user cannot view the user list | User Management | pass | Thành công
NG_04 | Paging appears when the user list exceeds the allowed number | User Management | pass | Thành công
NG_05 | Edit user information | User Management | pass | Thành công
NG_06-NG_07 | Update user information | User Management | pass | Thành công
NG_08-NG_09 | Delete user information | User Management | pass | Thành công
NG_10-NG_13 | Test the feature of searching for user information from any information available | User Management | pass | Thành công

## Integrated USER Management
No. | Test Requirement ID | Test Case ID | Test Objective | Pre-conditions | Step # | Step Action | Test Data | Expected Result | Notes
1 | F.3.1 | NG_01 | Kiểm tra xuất hiện danh sách người dùng | Danh sách người dùng tồn tại ít nhất 1 người và tài khoản admin mới có quyền được xem | 1 | Open login page | http://localhost:5173/sign-in
[5 empty] | 2 | Enter a valid email + valid password | email: phuc@gmail.com pass: 123456
[5 empty] | 3 | Press button <Đăng nhập> |  | Login successfully "Đăng nhập thành công" and go to home page
[5 empty] | 4 | Hover over the user icon which will show a popup and click on the "Quản lý hệ thống" button |  | The website will move to the admin page
[5 empty] | 5 | Click "Người dùng" to open book management page |  | User management page is displayed
[5 empty] | 6 | View full list of User |  | The book list is displayed completely and accurately
2 | F.3.2 | NG_02 | Xuất hiện thông tin chi tiết người dùng | Danh sách người dùng tồn tại ít nhất 1 người và tài khoản admin mới có quyền được xem | 1 | Open login page | http://localhost:5173/sign-in
[5 empty] | 2 | Enter a valid email + valid password | email: phuc@gmail.com pass: 123457
[5 empty] | 3 | Press button <Đăng nhập> |  | Login successfully "Đăng nhập thành công" and go to home page
[5 empty] | 4 | Hover over the user icon which will show a popup and click on the "Quản lý hệ thống" button |  | The website will move to the admin page
[5 empty] | 5 | Click "Người dùng" to open book management page |  | User management page is displayed
[5 empty] | 6 | View full list of User
[5 empty] | 7 | Chọn người dùng cần xem thông tin chi tiết | Tên người dùng:admin, email:admin@gmail.com, true, SĐT:888533121,Địa chỉ: Khuong Viet,Vai trò: nhân viên IT
[5 empty] | 8 | Chọn biểu tượng "Cây bút" trong cột hành động tương ứng với người dùng cần xem
[5 empty] | 9 | Bảng thông tin chi tiết người dùng xuất hiện | Tên người dùng:admin, email:admin@gmail.com, true, SĐT:888533121,Địa chỉ: Khuong Viet,Vai trò: nhân viên IT
3 | F.3.3 | NG_03 | Người dùng không thể xem danh sách người dùng | Danh sách người dùng tồn tại ít nhất 1 người và đăng nhập với tài khoản không có phân quyền | 1 | Open login page | http://localhost:5173/sign-in
[5 empty] | 2 | Enter a valid email + valid password | email: boi@gmail.com pass: 123456
[5 empty] | 3 | Press button <Đăng nhập> |  | Login successfully "Đăng nhập thành công" and go to home page
[5 empty] | 4 | Hover over the user icon which will show a popup and user does not see system management line
4 | F.3.4 | NG_04 | Xuất hiện phân trang khi danh sách người dùng vượt qua số lượng cho phép | Danh sách người dùng tồn tại ít nhất 1 người và nhiều hơn 10 người , tài khoản admin mới có quyền được xem | 1 | Open login page | http://localhost:5173/sign-in
[5 empty] | 2 | Enter a valid email + valid password | email: phuc@gmail.com pass: 123457
[5 empty] | 3 | Press button <Đăng nhập> |  | Login successfully "Đăng nhập thành công" and go to home page
[5 empty] | 4 | Hover over the user icon which will show a popup and click on the "Quản lý hệ thống" button |  | The website will move to the admin page
[5 empty] | 5 | Click "Người dùng" to open book management page |  | User management page is displayed
[5 empty] | 6 | View full list of User
[5 empty] | 7 | Lướt xuống cuối sẽ thấy danh sách phân trang
[5 empty] | 8 | Kích vào muỗi tên bên phải sẽ chuyển quua trang mới kèm theo danh sách người dùng mới
9
5 | F.3.5 | NG_05 | Chỉnh sửa thông tin người dùng | Danh sách người dùng tồn tại ít nhất 1 người, tài khoản admin mới có quyền được xem và chỉnh sửa | 1 | Open login page | http://localhost:5173/sign-in
[5 empty] | 2 | Enter a valid email + valid password | email: phuc@gmail.com pass: 123457
[5 empty] | 3 | Press button <Đăng nhập> |  | Login successfully "Đăng nhập thành công" and go to home page
[5 empty] | 4 | Hover over the user icon which will show a popup and click on the "Quản lý hệ thống" button |  | The website will move to the admin page
[5 empty] | 5 | Click "Người dùng" to open book management page |  | User management page is displayed
[5 empty] | 6 | View full list of User
[5 empty] | 7 | Chọn người dùng cần xem thông tin chi tiết | Tên người dùng:admin, email:admin@gmail.com, true, SĐT:888533121,Địa chỉ: Khuong Viet,Vai trò: nhân viên IT
[5 empty] | 8 | Chọn biểu tượng "Cây bút" trong cột hành động tương ứng với người dùng cần xem
[5 empty] | 9 | Bảng thông tin chi tiết người dùng xuất hiện | Tên người dùng:admin, email:admin@gmail.com, true, SĐT:888533121,Địa chỉ: Khuong Viet,Vai trò: nhân viên IT
[5 empty] | 10 | Chỉnh sửa thông tin người dùng | Tên người dùng:admin1, email:admin1@gmail.com, true, SĐT:888533121,Địa chỉ: Khuong Viet,Vai trò: nhân viên IT
[5 empty] | 11 | Chọn vào nút xác nhận |  | Thông báo cập nhật thành công
[5 empty] | 12 | Thông tin hiển thị người dùng đã được thay đổi so với thông tin ban đầu
6 | F.3.6 | NG_06-NG_07 | Cập nhật thông tin người dùng | Danh sách người dùng tồn tại ít nhất 1 người, tài khoản admin mới có quyền được xem và chỉnh sửa | 1 | Open login page | http://localhost:5173/sign-in
[5 empty] | 2 | Enter a valid email + valid password | email: phuc@gmail.com pass: 123458
[5 empty] | 3 | Press button <Đăng nhập> |  | Login successfully "Đăng nhập thành công" and go to home page
[5 empty] | 4 | Hover over the user icon which will show a popup and click on the "Quản lý hệ thống" button |  | The website will move to the admin page
[5 empty] | 5 | Click "Người dùng" to open book management page |  | User management page is displayed
[5 empty] | 6 | View full list of User
[5 empty] | 7 | Chọn người dùng cần xem thông tin chi tiết | Tên người dùng:admin, email:admin@gmail.com, true, SĐT:888533121,Địa chỉ: Khuong Viet,Vai trò: nhân viên IT
[5 empty] | 8 | Chọn biểu tượng "Cây bút" trong cột hành động tương ứng với người dùng cần xem
[5 empty] | 9 | Bảng thông tin chi tiết người dùng xuất hiện | Tên người dùng:admin, email:admin@gmail.com, true, SĐT:888533121,Địa chỉ: Khuong Viet,Vai trò: nhân viên IT
[5 empty] | 10 | Chỉnh sửa thông tin người dùng | Tên người dùng:admin1, email:admin1@gmail.com, true, SĐT:888533121,Địa chỉ: Khuong Viet,Vai trò: nhân viên IT
[5 empty] | 11 | Chọn vào nút xác nhận |  | Thông báo cập nhật thành công
[5 empty] | 12 | Thông tin hiển thị người dùng đã được thay đổi so với thông tin ban đầu
7 | F.3.7 | NG_08-NG09 | Xóa thông tin người dùng | Danh sách người dùng tồn tại ít nhất 1 người, tài khoản admin mới có quyền được xóa | 1 | Open login page | http://localhost:5173/sign-in
[5 empty] | 2 | Enter a valid email + valid password | email: phuc@gmail.com pass: 123459
[5 empty] | 3 | Press button <Đăng nhập> |  | Login successfully "Đăng nhập thành công" and go to home page
[5 empty] | 4 | Hover over the user icon which will show a popup and click on the "Quản lý hệ thống" button |  | The website will move to the admin page
[5 empty] | 5 | Click "Người dùng" to open book management page |  | User management page is displayed
[5 empty] | 6 | View full list of User
[5 empty] | 7 | Chọn người dùng cần xóa thông tin | Tên người dùng:admin, email:admin@gmail.com, true, SĐT:888533121,Địa chỉ: Khuong Viet,Vai trò: nhân viên IT
[5 empty] | 8 | Chọn biểu tượng "Thùng rác" trong cột hành động tương ứng với người dùng cần xóa
[5 empty] | 9 | Bảng xác nhận xóa người dùng xuất hiện |  | Hiện thông báo bạn có muốn xóa người dùng và yêu cầu chọn "yes" hoặc "no"
[5 empty] | 10 | Chọn "Yes" trong hộp thoại thông báo |  | Thông báo "Xóa người dùng thành công"
[5 empty] | 12 | Thông tin hiển thị người dùng đã được xóa và không còn hiện thông tin trên danh sách người dùng | Tên người dùng:admin, email:admin@gmail.com, true, SĐT:888533121,Địa chỉ: Khuong Viet,Vai trò: nhân viên IT
8 | F.3.8 | NG_10-NG13 | Kiểm tra tính năng tìm kiếm thông tin người dùng từ những thông tin bất kì có được | Danh sách người dùng tồn tại ít nhất 1 người, tài khoản admin mới có quyền tìm kiếm | 1 | Open login page | http://localhost:5173/sign-in
[5 empty] | 2 | Enter a valid email + valid password | email: phuc@gmail.com pass: 123460
[5 empty] | 3 | Press button <Đăng nhập> |  | Login successfully "Đăng nhập thành công" and go to home page
[5 empty] | 4 | Hover over the user icon which will show a popup and click on the "Quản lý hệ thống" button |  | The website will move to the admin page
[5 empty] | 5 | Click "Người dùng" to open book management page |  | User management page is displayed
[5 empty] | 6 | View full list of User
[5 empty] | 7 | Chọn vào biểu tượng "Kính lúp" trong những tiêu đề các cột
[5 empty] | 8 | Nhập thông tin vào một cột bất kì | Tên người dùng "admin" vào cột người dùng
[5 empty] | 9 | Nhấn search
[5 empty] | 10 | Danh sách người dùng xuất hiện | Tên người dùng:admin, email:admin@gmail.com, true, SĐT:888533121,Địa chỉ: Khuong Viet,Vai trò: nhân viên IT